## SFB NC600-16
NEW CONSTRUCTION
SFB NC 600-06 |  |  | SCHEDULE OF VALUES
|  | School District | TOLLESON UNION HIGH SCHOOL DISTRICT |  |  | SFB Meeting Date:
|  | SFB Project Number | 070514000-9999-006N
|  | Architect Name | ADM Group, Inc |  |  |  | SD
|  | CM @ Risk Name | Chasse Building Team |  |  |  | DD
|  | County | Maricopa County |  |  |  | GMP
|  | Grade Configuration | 9-12
|  | Square Footage | 311394 | enter only here | District Funded SF: |  | 275000
|  | Number of Buildings | 16 |  | Construction Schedule (number of days): |  | 520
|  | Student Capacity | 2926 |  | Prepared by: |  | Jeremy Keck
|  | Acres of Land | 69.319 |  | Prepared by Company: |  | Chasse Building Team
|  | Permitting (Name of County/City) | City of Avondale
|  | SFB Board Approved Budget |  | SFB site costs (included in GMP) |  | 7494485 | 0.069389 | AW-Y
|  | Grand GMP (Total of SFB Base Cost and District Cost) | 108007086 | Total GMP incld. SFB, District & Adj. Ways |  | 281.7702 |  | AW-N
|  |  |  | SFB Cost per SF | 15388% | 170.4631 | 10.6626 | 11.8397
|  |  |  | Cost per |  |  | Other On-Site
|  | Cells to be completed - as required |  | SFB Unit | SFB | District | Funding | Off-Site
|  |  | Quantity | (no markup) | Base Cost | Cost | (Adjacent Ways, etc.) | Adjacent Ways
| Div 1 | GENERAL CONDITIONS
| 01 50 00 | tempory facilites | 311394 | 1.4957 | 465754 | 515931 | 0 | 0
| 01 56 19 | dust control | 311394 | 7.6373 | 2378204 | 2634413 | 175071 | 194398 | GC'S
| 01 57 13 | track off pads | 311394 | 0.30472 | 94889 | 105111 |  |  | Testing/Inspections
| 6.077% | Division 1 total |  | 0.073256 | 2938847 | 3255455 | 175071 | 194398
| Div 2 | EXISTING CONDITIONS
| 02 21 13 | survey | 311394 | 0.21579 | 67197 | 74436 | 24000 | 40000
| 02 41 13 | site demolition/removal | 311394 | 0.32209 | 100297 | 111103
| 02 60 00 | soil treatment | 311394 | 0.04283 | 13337 | 14773
| 0.4121% | Division 2 total |  | 0.0045076 | 180831 | 200312 | 24000 | 40000
| Div 3 | CONCRETE
| 03 00 00 | footings/walls | 311394 | 0 | 0 | 0 | 0 | 0
| 03 00 00 | building | 311394 | 3.8401 | 1195776 | 1295424 | 0 | 0
| 03 20 00 | rebar | 311394 | 0 | 0 | 0 | 0 | 0
| 03 30 53 | slabs | 311394 | 3.903 | 1215360 | 1375469 | 1386955 | 729413
| 03 35 00 | sealed floors | 311394 | 0 | 0 | 0 | 0 | 0
| 03 40 00 | precast concrete | 311394 | 0 | 0 | 0 | 0 | 0
| 6.665% | Division 3 total |  | 0.060102 | 2411136 | 2670893 | 1386955 | 729413
| Div 4 | MASONRY
| 04 00 00 | masonry walls | 311394 | 10.6153 | 3305537 | 3669730
| 04 00 00 | masonry columns | 311394 | 0
| 04 05 19 | rebar | 311394 | 0
| 04 22 00 | site masonry | 311394 | 0.24085 | 75000 | 75000
| 04 22 00 | block fencing | 311394 | 0
| 04 43 00 | stonework | 311394 | 0.0095988 | 2989 | 3311
| 6.603% | Division 4 total |  | 0.084341 | 3383526 | 3748041 | 0 | 0
| Div 5 | METALS
| 05 00 00 | miscellaneous steel | 311394 | 0
| 05 10 00 | structural steel | 311394 | 10.7268 | 3340265 | 3700119
| 05 30 00 | metal decking | 311394 | 0
| 05 51 00 | stairs | 311394 | 0
| 05 70 00 | architectural steel | 311394 | 0
| 6.518% | Division 5 total |  | 0.083263 | 3340265 | 3700119 | 0 | 0
| Div 6 | WOODS/PLASTICS/COMPOSITES
| 06 10 00 | rough carpentry structure | 311394 | 0.14407 | 44861 | 49694
| 06 15 00 | wood decking | 311394 | 0
| 06 20 00 | finish carpentry | 311394 | 0
| 06 40 00 | millwork/casework | 311394 | 2.049 | 638044 | 706782
| 06 60 00 | plastic/glass fiber | 311394 | 0
| 1.333% | Division 6 total |  | 0.017023 | 682905 | 756476 | 0 | 0
| Div 7 | THERMAL/MOISTURE
| 07 10 00 | waterproofing/dampproofing | 311394 | 0
| 07 20 00 | building insulation | 311394 | 0.52471 | 163391 | 180994
| 07 21 00 | foam roof | 311394 | 0
| 07 25 00 | weather barrier | 311394 | 0
| 07 31 00 | roof shingles | 311394 | 0
| 07 32 00 | roof tiles | 311394 | 0
| 07 50 00 | membrane roofing | 311394 | 4.0024 | 1246308 | 1380575
| 07 60 00 | metal roof | 311394 | 0
| 07 60 00 | general sheet metal | 311394 | 2.8413 | 884777 | 980095 |  |  | METAL WALL PANELS
| 07 72 00 | roof accessories | 311394 | 0
| 07 81 00 | sprayed fireproofing | 311394 | 0
| 07 84 00 | firestopping | 311394 | 0
| 07 95 00 | roof expansion joint | 311394 | 0
| 07 92 00 | joint sealants | 311394 | 0.25955 | 80823 | 89531
| 4.635% | Division 7 total |  | 0.059209 | 2375299 | 2631195 | 0 | 0
| Div 8 | OPENINGS
| 81 10 00 | doors & frames | 311394 | 2.1601 | 672655 | 745122
| 08 33 00 | overhead doors | 311394 | 0.09549 | 29735 | 32938
| 08 40 00 | storefronts | 311394 | 2.6834 | 835608 | 925630
| 08 44 00 | curtain walls | 311394 | 0 |  |  |  |  | OPERABLE GLASS WALLS
| 08 50 00 | windows | 311394 | 0
| 08 60 00 | skylights | 311394 | 0.061437 | 19131 | 21192
| 08 70 00 | hardware | 311394 | 0
| 08 71 13 | automatic doors | 311394 | 0 |  |  |  |  | ACCESS CONTROLS
| 08 79 00 | knox box | 311394 | 0
| 08 80 00 | glass & glazing | 311394 | 0
| 3.039% | Division 8 total |  | 0.038814 | 1557129 | 1724882 | 0 | 0
| Div 9 | FINISHES
| 09 24 00 | stucco/EIFS systems | 311394 | 1.291 | 402006 | 445315
| 09 20 00 | interior metal studs/gypsum board | 311394 | 5.9474 | 1851983 | 2051502
| 09 22 00 | exterior metal stud framing | 311394 | 0
| 09 23 00 | decorative plaster | 311394 | 0
| 09 51 00 | acoustical ceilings | 311394 | 1.7135 | 533563 | 591045
| 09 31 00 | ceramic tile | 311394 | 0
| 09 65 00 | resilient flooring | 311394 | 0
| 09 68 00 | carpet | 311394 | 3.9543 | 1231341 | 1363997 |  |  | 300000
| 09 64 00 | wood floors | 311394 | 0 |  |  |  |  | 250000
| 09 67 00 | epoxy | 311394 | 0
| 09 80 00 | sound panels | 311394 | 0
| 09 90 00 | painting | 311394 | 1.7247 | 537075 | 594936
| 09 77 00 | fiberglass reinforced panels | 311394 | 0
| 8.891% | Division 9 total |  | 0.11357 | 4555968 | 5046795 | 0 | 0
| Div 10 | SPECIALTIES
| 10 11 00 | visual display boards | 311394 | 0
| 10 14 00 | signage | 311394 | 0.57356 | 178604 | 197846
| 10 21 13 | toilet partitions & accessories | 311394 | 0.71115 | 221449 | 245307
| 10 21 23 | cubicle track & curtain | 311394 | 0
| 10 22 26 | operable partitions/walls | 311394 | 0
| 10 26 00 | wall protection | 311394 | 0
| 10 44 00 | fire exttinguishers & cabinets | 311394 | 0
| 10 50 00 | lockers | 311394 | 0
| 10 56 13 | storage shelving | 311394 | 0
| 10 73 00 | shelters | 311394 | 0
| 10 73 13 | awnings | 311394 | 0
| 10 73 13 | canopy/ramada | 311394 | 0.50601 | 157568 | 175082
| 10 75 00 | flagpoles | 311394 | 0.016057 | 5000 | 5000
| 1.098% | Division 10 total |  | 0.014024 | 562621 | 623235 | 0 | 0
| Div 11 | EQUIPMENT
| 11 16 16 | floor safe | 311394 | 0
| 11 41 00 | kitchen equipment | 311394 | 1.7136 | 533599 | 591085
| 11 51 00 | library equipment | 311394 | 0
| 11 52 00 | audio/visual equipment | 311394 | 0
| 11 52 13 | projection screens | 311394 | 0
| 11 53 13 | fume hoods | 311394 | 0
| 11 61 43 | stage curtain/equipment | 311394 | 0.53326 | 166055 | 183945
| 11 66 00 | sports/PE equipment | 311394 | 4.0872 | 1272728 | 1409842
| 11 68 00 | playground equipment | 311394 | 0
| 11 68 23 | site basketball courts | 311394 | 0
| 11 68 33 | ballfield backstop | 311394 | 0 |  |  |  |  | TENNIS
| 11 68 33 | sports fields | 311394 | 1.7462 | 543750 | 602330 |  |  | RUNNING TRACK
| 4.91% | Division 11 total |  | 0.062719 | 2516132 | 2787202 | 0 | 0
| Div 12 | FURNISHINGS
| 12 20 00 | window coverings | 311394 | 0.22854 | 71167 | 78833
| 12 31 00 | metal casework | 311394 | 0
| 12 32 16 | plastic laminate casework | 311394 | 0
| 12 61 00 | auditorium seating | 311394 | 0
| 12 93 13 | bike racks | 311394 | 0
| 12 93 23 | trash enclosures | 311394 | 0
| 0.1389% | Division 12 total |  | 0.001774 | 71167 | 78833 | 0 | 0
| Div 13 | SPECIAL CONST
| 13 00 00 | equipment/storage enclosures | 311394 | 0 |  |  |  |  | BARN & GREENHOUSE
| 13 11 00 | swimming pools | 311394 | 0
| 13 34 16 | bleachers | 311394 | 0
| 13 34 19 | metal buildings | 311394 | 0
| 0% | Division 13 total |  | 0 | 0 | 0 | 0 | 0
| Div 14 | CONVEYING
| 14 00 00 | material handling | 311394 | 0
| 14 20 00 | elevators | 311394 | 0.39538 | 123118 | 136382
| 14 42 00 | wheelchair lifts | 311394 | 0
| 0.2403% | Division 14 total |  | 0.003069 | 123118 | 136382 | 0 | 0
| Div 21 | FIRE SUPPRESSION
| 21 10 00 | fire protection/sprinklers | 311394 | 1.3477 | 419652 | 464863
| 0.8189% | Division 21 total |  | 0.010461 | 419652 | 464863 | 0 | 0
| Div 22 | PLUMBING
| 22 11 00 | supply piping | 311394 | 5.0366 | 1568377 | 1737342
| 22 13 00 | waste water piping | 311394 | 0
| 22 31 00 | water treatment (softner) | 311394 | 0
| 22 32 00 | water treatment (filtered) | 311394 | 0
| 22 35 00 | water heaters | 311394 | 0
| 22 42 00 | plumbing fixtures | 311394 | 0
| 3.061% | Division 22 total |  | 0.039095 | 1568377 | 1737342 | 0 | 0
| Div 23 | MECHANICAL
| 23 07 13 | mechanical insulation | 311394 | 0
| 23 50 00 | HVAC - central plant (cooling) | 311394 | 12.5176 | 3897890 | 4366298
| 23 60 00 | HVAC - central plant (heating) | 311394 | 0
| 23 76 00 | HVAC - evaporative | 311394 | 0
| 23 80 00 | HVAC - package units | 311394 | 0
| 23 81 26 | HVAC - split system | 311394 | 0
| 7.652% | Division 23 total |  | 0.097162 | 3897890 | 4366298 | 0 | 0
| Div 25 | INTEGRATED AUTOMATION
| 25 50 00 | EMS | 311394 | 1.4451 | 450000 | 450000
| 0.8333% | Division 25 total |  | 0.011217 | 450000 | 450000 | 0 | 0
| Div 26 | ELECTRICAL
| 26 10 00 | site electrical | 311394 | 2.4085 | 750000 | 750000 |  | 641835
| 26 10 00 | electrical | 311394 | 11.3387 | 3530811 | 3991992
| 26 30 00 | generators | 311394 | 0 |  |  |  |  | SOLAR PANELS
| 26 56 00 | exterior lighting | 311394 | 0
| 8.948% | Division 26 total |  | 0.10671 | 4280811 | 4741992 | 0 | 641835
| Div 27 | COMMUNICATIONS
| 27 20 00 | data cabling | 311394 | 0.56199 | 175000 | 175000
| 27 24 00 | TV cabling | 311394 | 0.71488 | 222609 | 327391
| 27 30 00 | intercom | 311394 | 0.40142 | 125000 | 125000
| 27 32 13 | communications/phone | 311394 | 0.80284 | 250000 | 250000 |  |  | WIRELESS CLOCKS
| 1.528% | Division 27 total |  | 0.019259 | 772609 | 877391 | 0 | 0
| Div 28 | SAFETY AND SECURITY
| 28 10 00 | security system | 311394 | 0.24085 | 75000 | 75000
| 28 20 00 | surveillance/alarm | 311394 | 0.40142 | 125000 | 125000
| 28 31 00 | fire alarm system | 311394 | 0.65558 | 204145 | 226138
| 0.7687% | Division 28 total |  | 0.010074 | 404145 | 426138 | 0 | 0
| Div 31 | EARTHWORK
| 31 23 00 | earthwork/mass excavation | 311394 | 2.5969 | 808658 | 922709
| 31 23 00 | import/export dirt | 311394 | 0
| 31 31 00 | soil treatment - termite | 311394 | 0 |  |  |  |  | WITH/00 26 00
| 1.603% | Division 31 total |  | 0.020157 | 808658 | 922709 | 0 | 0
| Div 32 | EXTERIOR IMPROVEMENTS
| 32 00 00 | parking | 311394 | 0
| 32 00 00 | unusal site conditions | 311394 | 0
| 32 10 00 | asphalt/paving | 311394 | 0.80284 | 250000 | 250000 | 1282438 | 923148
| 32 13 00 | site concrete | 311394 | 0
| 32 13 00 | sidewalks | 311394 | 0
| 32 17 00 | striping/signage | 311394 | 0
| 32 31 13 | chainlink fencing | 311394 | 0
| 32 31 19 | wrought iron fencing | 311394 | 1.8878 | 587861 | 651192
| 32 32 00 | retaining walls | 311394 | 0
| 32 80 00 | irrigation | 311394 | 0 |  |  |  |  | GREENSCREEN
| 32 90 00 | landscaping | 311394 | 3.163 | 984939 | 1091049 |  | 218214
| 5.776% | Division 32 total |  | 0.045437 | 1822800 | 1992241 | 1282438 | 1141362
| Div 33 | UTILITIES
| 33 00 00 | site utilities | 311394 | 2.6901 | 837674 | 927918 |  | 438136
| 33 21 00 | wells | 311394 | 0
| 33 32 16 | lift station | 311394 | 0
| 33 36 00 | septic system | 311394 | 0
| 33 40 00 | stormwater/drainage | 311394 | 0
| 33 49 23 | drywells | 311394 | 0.49993 | 155675 | 172447
| 2.344% | Division 33 total |  | 0.024761 | 993349 | 1100365 | 0 | 438136
|  | Subtotal | 90610002 |  | 40117235 | 44439159 | 2868464 | 3185144
| 6.0133e-10 | Contractor Fee |  | 6.495% | 2605517 | 2886212 | 180533 | 200466
| 2.9566e-10 | Contactor Contingency |  | 3.193% | 1281082 | 1419095
| 1.493e-10 | Builders Risk/Liability Insurance |  | 1.613% | 646904 | 716596 | 44824 | 49772
| 1.2165e-10 | Performance & Payment Bonds |  | 1.314% | 527107 | 583893 | 36523 | 40555
| 6.3258e-10 | Sales Tax |  | 6.832% | 2740955 | 3036245 | 189919 | 210886
|  | Subtotal | 108007086 |  | 47918800 | 53081200 | 3320263 | 3686823
| 0.83893 | Grand Guaranteed Maximum Price (GMP) | 108007086 |  | (Total of SFB Base Cost and District Cost)