## SFB
NEW CONSTRUCTION
SFB NC 600-06 |  |  | SCHEDULE OF VALUES
|  | School District | QUEEN CREEK UNIFIED SCHOOL DISTRICT NO. 95 |  |  | SFB Meeting Date:
|  | SFB Project Number | #070514000-9999-005N
|  | Architect Name | DLR Group |  |  |  | SD
|  | CM @ Risk Name | Chasse Building Team |  |  |  | DD
|  | County | Maricopa County |  |  |  | GMP
|  | Grade Configuration | 1-5
|  | Square Footage | 88421 | enter only here | District Funded SF:
|  | Number of Buildings | 4 |  | Construction Schedule (number of days): |  | 335
|  | Student Capacity | 900 |  | Prepared by: |  | Chris Yncera
|  | Acres of Land | 15.7457 |  | Prepared by Company: |  | Chasse Building Team GMP#2
|  | Permitting (Name of County/City) | City of Mesa
|  | SFB Board Approved Budget |  | SFB site costs (included in GMP) |  | 456065 | 0.024835 | AW-Y
|  | Grand GMP (Total of SFB Base Cost and District Cost) | 18364067 | Total GMP incld. SFB, District & Adj. Ways |  | 170.4375 |  | AW-N
|  |  |  | SFB Cost per SF | 7776% | 124.756 | 5.1699 | 0
|  |  |  | Cost per |  |  | Other On-Site
|  | Cells to be completed - as required |  | SFB Unit | SFB | District | Funding | Off-Site
|  |  | Quantity | (no markup) | Base Cost | Cost | (Adjacent Ways, etc.) | Adjacent Ways
| Div 1 | GENERAL CONDITIONS
| 01 50 00 | tempory facilites | 88421 | 0
| 01 56 19 | dust control | 88421 | 2.5858 | 228643 | 366896 | 36570 |  | GC's and GR's | 183448
| 01 57 13 | track off pads | 88421 | 0
| 3.442% | Division 1 total |  | 0.039512 | 228643 | 366896 | 36570 | 0
| Div 2 | EXISTING CONDITIONS
| 02 21 13 | survey | 88421 | 0.046855 | 4143 | 6647
| 02 41 13 | site demolition/removal | 88421 | 0
| 02 60 00 | soil treatment | 88421 | 0
| 0.05876% | Division 2 total |  | 0.00071596 | 4143 | 6647 | 0 | 0
| Div 3 | CONCRETE
| 03 00 00 | footings/walls | 88421 | 0
| 03 00 00 | building | 88421 | 2.6645 | 235594 | 468599
| 03 20 00 | rebar | 88421 | 0
| 03 30 53 | slabs | 88421 | 1.6964 | 150000 | 150000 | 122055
| 03 35 00 | sealed floors | 88421 | 0
| 03 40 00 | precast concrete | 88421 | 0
| 6.133% | Division 3 total |  | 0.066635 | 385594 | 618599 | 122055 | 0
| Div 4 | MASONRY
| 04 00 00 | masonry walls | 88421 | 4.8641 | 430088 | 689980
| 04 00 00 | masonry columns | 88421 | 0
| 04 05 19 | rebar | 88421 | 0
| 04 22 00 | site masonry | 88421 | 0
| 04 22 00 | block fencing | 88421 | 0
| 04 43 00 | stonework | 88421 | 0
| 6.099% | Division 4 total |  | 0.074324 | 430088 | 689980 | 0 | 0
| Div 5 | METALS
| 05 00 00 | miscellaneous steel | 88421 | 0
| 05 10 00 | structural steel | 88421 | 7.0168 | 620429 | 995338
| 05 30 00 | metal decking | 88421 | 0
| 05 51 00 | stairs | 88421 | 0
| 05 70 00 | architectural steel | 88421 | 0
| 8.799% | Division 5 total |  | 0.10722 | 620429 | 995338 | 0 | 0
| Div 6 | WOODS/PLASTICS/COMPOSITES
| 06 10 00 | rough carpentry structure | 88421 | 0.069757 | 6168 | 9894
| 06 15 00 | wood decking | 88421 | 0
| 06 20 00 | finish carpentry | 88421 | 0
| 06 40 00 | millwork/casework | 88421 | 1.8628 | 164714 | 264246
| 06 60 00 | plastic/glass fiber | 88421 | 0
| 2.423% | Division 6 total |  | 0.02953 | 170882 | 274140 | 0 | 0
| Div 7 | THERMAL/MOISTURE
| 07 10 00 | waterproofing/dampproofing | 88421 | 0
| 07 20 00 | building insulation | 88421 | 0.53196 | 47036 | 75459
| 07 21 00 | foam roof | 88421 | 0
| 07 25 00 | weather barrier | 88421 | 0
| 07 31 00 | roof shingles | 88421 | 0
| 07 32 00 | roof tiles | 88421 | 0
| 07 50 00 | membrane roofing | 88421 | 2.2122 | 195609 | 313810
| 07 60 00 | metal roof | 88421 | 0
| 07 60 00 | general sheet metal | 88421 | 0.56467 | 49929 | 80101
| 07 72 00 | roof accessories | 88421 | 0.099773 | 8822 | 14153
| 07 81 00 | sprayed fireproofing | 88421 | 0
| 07 84 00 | firestopping | 88421 | 0
| 07 95 00 | roof expansion joint | 88421 | 0
| 07 92 00 | joint sealants | 88421 | 0.35814 | 31667 | 50803
| 4.723% | Division 7 total |  | 0.057557 | 333063 | 534326 | 0 | 0
| Div 8 | OPENINGS
| 81 10 00 | doors & frames | 88421 | 1.5194 | 134346 | 215529 |  |  | Early procurement HM
| 08 33 00 | overhead doors | 88421 | 0.075785 | 6701 | 10750
| 08 40 00 | storefronts | 88421 | 1.5317 | 135431 | 217269
| 08 44 00 | curtain walls | 88421 | 0
| 08 50 00 | windows | 88421 | 0
| 08 60 00 | skylights | 88421 | 0
| 08 70 00 | hardware | 88421 | 0
| 08 71 13 | automatic doors | 88421 | 0
| 08 79 00 | knox box | 88421 | 0
| 08 80 00 | glass & glazing | 88421 | 0
| 3.921% | Division 8 total |  | 0.047779 | 276478 | 443548 | 0 | 0
| Div 9 | FINISHES
| 09 24 00 | stucco/EIFS systems | 88421 | 0
| 09 20 00 | interior metal studs/gypsum board | 88421 | 3.8559 | 340944 | 546968
| 09 22 00 | exterior metal stud framing | 88421 | 0
| 09 23 00 | decorative plaster | 88421 | 0
| 09 51 00 | acoustical ceilings | 88421 | 1.1955 | 105711 | 169589
| 09 31 00 | ceramic tile | 88421 | 0
| 09 65 00 | resilient flooring | 88421 | 2.3298 | 205999 | 330478
| 09 68 00 | carpet | 88421 | 0
| 09 64 00 | wood floors | 88421 | 0
| 09 67 00 | epoxy | 88421 | 0
| 09 80 00 | sound panels | 88421 | 0
| 09 90 00 | painting | 88421 | 1.2625 | 111630 | 179085
| 09 77 00 | fiberglass reinforced panels | 88421 | 0
| 10.84% | Division 9 total |  | 0.13208 | 764284 | 1226120 | 0 | 0
| Div 10 | SPECIALTIES
| 10 11 00 | visual display boards | 88421 | 0
| 10 14 00 | signage | 88421 | 0.58594 | 51809 | 83116
| 10 21 13 | toilet partitions & accessories | 88421 | 0.59687 | 52776 | 84668
| 10 21 23 | cubicle track & curtain | 88421 | 0
| 10 22 26 | operable partitions/walls | 88421 | 0
| 10 26 00 | wall protection | 88421 | 0
| 10 44 00 | fire exttinguishers & cabinets | 88421 | 0
| 10 50 00 | lockers | 88421 | 0
| 10 56 13 | storage shelving | 88421 | 0
| 10 73 00 | shelters | 88421 | 0
| 10 73 13 | awnings | 88421 | 0
| 10 73 13 | canopy/ramada | 88421 | 0
| 10 75 00 | flagpoles | 88421 | 0
| 1.483% | Division 10 total |  | 0.018073 | 104585 | 167784 | 0 | 0
| Div 11 | EQUIPMENT
| 11 16 16 | floor safe | 88421 | 0
| 11 41 00 | kitchen equipment | 88421 | 1.3843 | 122403 | 196368
| 11 51 00 | library equipment | 88421 | 0
| 11 52 00 | audio/visual equipment | 88421 | 0
| 11 52 13 | projection screens | 88421 | 0
| 11 53 13 | fume hoods | 88421 | 0
| 11 61 43 | stage curtain/equipment | 88421 | 0
| 11 66 00 | sports/PE equipment | 88421 | 0.38405 | 33958 | 54477
| 11 68 00 | playground equipment | 88421 | 0.95015 | 84013 | 134924
| 11 68 23 | site basketball courts | 88421 | 0
| 11 68 33 | ballfield backstop | 88421 | 0
| 11 68 33 | sports fields | 88421 | 0
| 3.41% | Division 11 total |  | 0.041539 | 240374 | 385769 | 0 | 0
| Div 12 | FURNISHINGS
| 12 20 00 | window coverings | 88421 | 0.17153 | 15167 | 24333
| 12 31 00 | metal casework | 88421 | 0
| 12 32 16 | plastic laminate casework | 88421 | 0
| 12 61 00 | auditorium seating | 88421 | 0
| 12 93 13 | bike racks | 88421 | 0
| 12 93 23 | trash enclosures | 88421 | 0
| 0.2151% | Division 12 total |  | 0.002621 | 15167 | 24333 | 0 | 0
| Div 13 | SPECIAL CONST
| 13 00 00 | equipment/storage enclosures | 88421 | 0
| 13 11 00 | swimming pools | 88421 | 0
| 13 34 16 | bleachers | 88421 | 0
| 13 34 19 | metal buildings | 88421 | 0
| 0% | Division 13 total |  | 0 | 0 | 0 | 0 | 0
| Div 14 | CONVEYING
| 14 00 00 | material handling | 88421 | 0
| 14 20 00 | elevators | 88421 | 0.17107 | 15126 | 24266 |  |  | Early procurement
| 14 42 00 | wheelchair lifts | 88421 | 0
| 0.2145% | Division 14 total |  | 0.0026139 | 15126 | 24266 | 0 | 0
| Div 21 | FIRE SUPPRESSION
| 21 10 00 | fire protection/sprinklers | 88421 | 0.82442 | 72896 | 116945
| 1.034% | Division 21 total |  | 0.012597 | 72896 | 116945 | 0 | 0
| Div 22 | PLUMBING
| 22 11 00 | supply piping | 88421 | 0
| 22 13 00 | waste water piping | 88421 | 0
| 22 31 00 | water treatment (softner) | 88421 | 0
| 22 32 00 | water treatment (filtered) | 88421 | 0
| 22 35 00 | water heaters | 88421 | 0
| 22 42 00 | plumbing fixtures | 88421 | 3.2349 | 286030 | 458870
| 4.056% | Division 22 total |  | 0.049429 | 286030 | 458870 | 0 | 0
| Div 23 | MECHANICAL
| 23 07 13 | mechanical insulation | 88421 | 0
| 23 50 00 | HVAC - central plant (cooling) | 88421 | 0
| 23 60 00 | HVAC - central plant (heating) | 88421 | 0
| 23 76 00 | HVAC - evaporative | 88421 | 0
| 23 80 00 | HVAC - package units | 88421 | 9.9153 | 876722 | 1406503
| 23 81 26 | HVAC - split system | 88421 | 0
| 12.43% | Division 23 total |  | 0.15151 | 876722 | 1406503 | 0 | 0
| Div 25 | INTEGRATED AUTOMATION
| 25 50 00 | EMS | 88421 | 0
| 0% | Division 25 total |  | 0 | 0 | 0 | 0 | 0
| Div 26 | ELECTRICAL
| 26 10 00 | site electrical | 88421 | 0
| 26 10 00 | electrical | 88421 | 6.4833 | 573259 | 919664
| 26 30 00 | generators | 88421 | 0
| 26 56 00 | exterior lighting | 88421 | 0
| 8.13% | Division 26 total |  | 0.099066 | 573259 | 919664 | 0 | 0
| Div 27 | COMMUNICATIONS
| 27 20 00 | data cabling | 88421 | 1.2216 | 108015 | 173285
| 27 24 00 | TV cabling | 88421 | 0
| 27 30 00 | intercom | 88421 | 0
| 27 32 13 | communications/phone | 88421 | 0
| 1.532% | Division 27 total |  | 0.018666 | 108015 | 173285 | 0 | 0
| Div 28 | SAFETY AND SECURITY
| 28 10 00 | security system | 88421 | 0
| 28 20 00 | surveillance/alarm | 88421 | 0
| 28 31 00 | fire alarm system | 88421 | 0.65135 | 57593 | 92395
| 0.8167% | Division 28 total |  | 0.0099527 | 57593 | 92395 | 0 | 0
| Div 31 | EARTHWORK
| 31 23 00 | earthwork/mass excavation | 88421 | 0
| 31 23 00 | import/export dirt | 88421 | 0
| 31 31 00 | soil treatment - termite | 88421 | 0.025209 | 2229 | 3575
| 0.03161% | Division 31 total |  | 0.0003852 | 2229 | 3575 | 0 | 0
| Div 32 | EXTERIOR IMPROVEMENTS
| 32 00 00 | parking | 88421 | 0
| 32 00 00 | unusal site conditions | 88421 | 0
| 32 10 00 | asphalt/paving | 88421 | 1.053 | 93106 | 149368 | 241484
| 32 13 00 | site concrete | 88421 | 0
| 32 13 00 | sidewalks | 88421 | 0
| 32 17 00 | striping/signage | 88421 | 0
| 32 31 13 | chainlink fencing | 88421 | 0
| 32 31 19 | wrought iron fencing | 88421 | 1.1526 | 101916 | 163500
| 32 32 00 | retaining walls | 88421 | 0
| 32 80 00 | irrigation | 88421 | 0
| 32 90 00 | landscaping | 88421 | 1.1214 | 99153 | 159069
| 5.487% | Division 32 total |  | 0.050837 | 294175 | 471937 | 241484 | 0
| Div 33 | UTILITIES
| 33 00 00 | site utilities | 88421 | -0.82701 | -73125 | -117312
| 33 21 00 | wells | 88421 | 0
| 33 32 16 | lift station | 88421 | 0
| 33 36 00 | septic system | 88421 | 0
| 33 40 00 | stormwater/drainage | 88421 | 0
| 33 49 23 | drywells | 88421 | 0
| -1.037% | Division 33 total |  | -0.012637 | -73125 | -117312 | 0 | 0
|  | Subtotal | 15470367 |  | 5786650 | 9283608 | 400109 | 0
| 3.2353e-09 | Contractor Fee |  | 5.941% | 343799 | 551548 | 22856
| 2.2019e-09 | Contactor Contingency |  | 4.044% | 233985 | 375375
| 9.0587e-10 | Builders Risk/Liability Insurance |  | 1.664% | 96264 | 154434 | 6399
| 7.1176e-10 | Performance & Payment Bonds |  | 1.307% | 75636 | 121341 | 5028
| 3.1953e-09 | Sales Tax |  | 5.868% | 339558 | 544745 | 22732
|  | Subtotal | 18364067 |  | 6875892 | 11031051 | 457124 | 0
| 0.84243 | Grand Guaranteed Maximum Price (GMP) | 18364067 |  | (Total of SFB Base Cost and District Cost)