## SFB NC600-16 GMP 2
NEW CONSTRUCTION
SFB NC 600-06 |  |  | SCHEDULE OF VALUES
|  | School District | Chandler Unified School District |  |  | SFB Meeting Date:
SFB Project Number
|  | Architect Name | HDA Architects |  |  |  | SD
|  | CM @ Risk Name | McCArthy Buildng Companies Inc. |  |  |  | DD
|  | County | Maricopa |  |  |  | GMP
|  | Grade Configuration | K-6
|  | Square Footage | 88587 | enter only here | District Funded SF:
|  | Number of Buildings | one |  | Construction Schedule (number of days): |  | 240
|  | Student Capacity |  |  | Prepared by: |  | M Boyd
|  | Acres of Land | 14.51 Acres Gross |  | Prepared by Company: |  | McCarthy Building Companies
|  | Permitting (Name of County/City) | Town of Gilbet, AZ
|  | SFB Board Approved Budget |  | SFB site costs (included in GMP) |  | 0 | 0 | AW-Y
|  | Grand GMP (Total of SFB Base Cost and District Cost) | 22998856 | Total GMP incld. SFB, District & Adj. Ways |  | 217.3198 |  | AW-N
|  |  |  | SFB Cost per SF | 0% | 227.5338 | 12.0901 | 19.995
|  |  |  | Cost per |  |  | Other On-Site |  | Adjacent Ways
|  | Cells to be completed - as required |  | SFB Unit | SFB | District | Funding | Off-Site | On-Site | Off-Site
|  |  | Quantity | (no markup) | Base Cost | Cost | (Adjacent Ways, etc.) | Adjacent Ways
| Div 1 | GENERAL CONDITIONS
| 01 50 00 | tempory facilites |  | 0 |  | 823368 | 41798 | 69128
| 01 56 19 | dust control |  | 0 | 0 | incl w/ Earthwork
| 01 57 13 | track off pads |  | 0 | 0 | incl w/ Earthwork
| 4.062% | Division 1 total |  |  | 0 | 823368 | 41798 | 69128
| Div 2 | EXISTING CONDITIONS
| 02 21 13 | survey |  | 0 | 0 | 44876 | 2528 | 5626
| 02 41 13 | site demolition/removal |  | 0 | 0 | Incl. with Earthwork
| 02 60 00 | soil treatment |  | 0 | 0 | 18368
| 0.3104% | Division 2 total |  |  | 0 | 63244 | 2528 | 5626
| Div 3 | CONCRETE
| 03 00 00 | footings/walls |  | 0 | 0 | Incl. with Building
| 03 00 00 | building |  | 0 | 0 | 825956
| 03 20 00 | rebar |  | 0 | 0 | Incl. with Building
| 03 30 53 | slabs |  | 0 | 0 | Incl. with Building
| 03 35 00 | sealed floors |  | 0 | 0 | Incl. with Flooring
| 03 40 00 | precast concrete |  | 0 | 0 | Incl. with Mason
| 7.559% | Division 3 total |  |  | 0 | 825956 | 0 | 0
| Div 4 | MASONRY
| 04 00 00 | masonry walls |  | 0 | 0 | 1363731
| 04 00 00 | masonry columns |  | 0 | 0 | Incl. with Mason
| 04 05 19 | rebar |  | 0 | 0 | Incl. with Mason
| 04 22 00 | site masonry |  | 0 | 0 | Incl. with Mason
| 04 22 00 | block fencing |  | 0 | 0 | Incl. with Mason
| 04 43 00 | stonework |  | 0 | 0 | Incl. with Mason
| 5.93% | Division 4 total |  |  | 0 | 1363731 | 0 | 0
| Div 5 | METALS
| 05 00 00 | miscellaneous steel |  | 0 | 0 | 253339
| 05 10 00 | structural steel |  | 0 | 0 | 1325724
| 05 30 00 | metal decking |  | 0 | 0 | Incl. with ST. Steel
| 05 51 00 | stairs |  | 0 | 0 | Incl. with ST. Steel
| 05 70 00 | architectural steel |  | 0 | 0 | Incl. with ST. Steel
| 6.866% | Division 5 total |  |  | 0 | 1579063 | 0 | 0
| Div 6 | WOODS/PLASTICS/COMPOSITES
| 06 10 00 | rough carpentry structure |  | 0 | 0 | 88122
| 06 15 00 | wood decking |  | 0 | 0 | 0
| 06 20 00 | finish carpentry |  | 0 | 0 | 0
| 06 40 00 | millwork/casework |  | 0 | 0 | 574341
| 06 60 00 | plastic/glass fiber |  | 0 | 0 | 0
| 3.278% | Division 6 total |  |  | 0 | 662463 | 0 | 0
| Div 7 | THERMAL/MOISTURE
| 07 10 00 | waterproofing/dampproofing |  | 0 | 0 | 189295
| 07 20 00 | building insulation |  | 0 | 0 | 219923
| 07 21 00 | foam roof |  | 0 | 0 | 1007746
| 07 25 00 | weather barrier |  | 0 | 0 | 0
| 07 31 00 | roof shingles |  | 0 | 0 | 0
| 07 32 00 | roof tiles |  | 0 | 0 | 0
| 07 50 00 | membrane roofing |  | 0 | 0 | 0
| 07 60 00 | metal roof |  | 0 | 0 | Incl with Foam Roof
| 07 60 00 | general sheet metal |  | 0 | 0 | Incl with Foam Roof
| 07 72 00 | roof accessories |  | 0 | 0 | 0
| 07 81 00 | sprayed fireproofing |  | 0 | 0 | 0
| 07 84 00 | firestopping |  | 0 | 0 | Incl. with Joint Seal.
| 07 95 00 | roof expansion joint |  | 0 | 0 | Incl with Foam Roof
| 07 92 00 | joint sealants |  | 0 | 0 | Incl. with W. P.
| 6.161% | Division 7 total |  |  | 0 | 1416964 | 0 | 0
| Div 8 | OPENINGS
| 81 10 00 | doors & frames |  | 0 | 0 | 525905
| 08 33 00 | overhead doors |  | 0 | 0 | 19083
| 08 40 00 | storefronts |  | 0 | 0 | Incl. with Glass
| 08 44 00 | curtain walls |  | 0 | 0 | 0
| 08 50 00 | windows |  | 0 | 0 | Incl with Doors
| 08 60 00 | skylights |  | 0 | 0 | 50607
| 08 70 00 | hardware |  | 0 | 0 | Incl. with Doors
| 08 71 13 | automatic doors |  | 0 | 0 | Incl. with Doors
| 08 79 00 | knox box |  | 0 | 0 | 0
| 08 80 00 | glass & glazing |  | 0 | 0 | 91325
| 2.59% | Division 8 total |  |  | 0 | 686920 | 0 | 0
| Div 9 | FINISHES
| 09 24 00 | stucco/EIFS systems |  | 0 | 0 | 0
| 09 20 00 | interior metal studs/gypsum board |  | 0 | 0 | 880746
| 09 22 00 | exterior metal stud framing |  | 0 | 0 | 0
| 09 23 00 | decorative plaster |  | 0 | 0 | 0
| 09 51 00 | acoustical ceilings |  | 0 | 0 | 296317
| 09 31 00 | ceramic tile |  | 0 | 0 | 90914
| 09 65 00 | resilient flooring |  | 0 | 0 | 356592
| 09 68 00 | carpet |  | 0 | 0 | Incl. with Resilient
| 09 64 00 | wood floors |  | 0 | 0 | 0
| 09 67 00 | epoxy |  | 0 | 0 | Incl. with Resilient
| 09 80 00 | sound panels |  | 0 | 0 | Incl with Acoustic
| 09 90 00 | painting |  | 0 | 0 | 205382
| 09 77 00 | fiberglass reinforced panels |  | 0 | 0 | Incl with Kitchen
| 7.957% | Division 9 total |  |  | 0 | 1829951 | 0 | 0
| Div 10 | SPECIALTIES
| 10 11 00 | visual display boards |  | 0 | 0 | 47023
| 10 14 00 | signage |  | 0 | 0 | 31981
| 10 21 13 | toilet partitions & accessories |  | 0 | 0 | 74124
| 10 21 23 | cubicle track & curtain |  | 0 | 0 | Incl with Partitions
| 10 22 26 | operable partitions/walls |  | 0 | 0 | 0
| 10 26 00 | wall protection |  | 0 | 0 | 3108
| 10 44 00 | fire exttinguishers & cabinets |  | 0 | 0 | Incl. with Partitions
| 10 50 00 | lockers |  | 0 | 0 | 0
| 10 56 13 | storage shelving |  | 0 | 0 | 0
| 10 73 00 | shelters |  | 0 | 0 | 50638
| 10 73 13 | awnings |  | 0 | 0 | 0
| 10 73 13 | canopy/ramada |  | 0 | 0 | 0
| 10 75 00 | flagpoles |  | 0 | 0 | 6737
| 0.9288% | Division 10 total |  |  | 0 | 213611 | 0 | 0
| Div 11 | EQUIPMENT
| 11 16 16 | floor safe |  | 0 | 0 | 939
| 11 41 00 | kitchen equipment |  | 0 | 0 | 185912
| 11 51 00 | library equipment |  | 0 | 0 | 0
| 11 52 00 | audio/visual equipment |  | 0 | 0 | 0
| 11 52 13 | projection screens |  | 0 | 0 | Incl. With A/V
| 11 53 13 | fume hoods |  | 0 | 0 | Incl. with Kitchen
| 11 61 43 | stage curtain/equipment |  | 0 | 0 | 16442
| 11 66 00 | sports/PE equipment |  | 0 | 0 | 48533
| 11 68 00 | playground equipment |  | 0 | 0 | 311801
| 11 68 23 | site basketball courts |  | 0 | 0 | W/ Athletic Equip.
| 11 68 33 | ballfield backstop |  | 0 | 0 | With Site fencing
| 11 68 33 | sports fields |  | 0 | 0 | With Earthwork / LS
| 2.451% | Division 11 total |  |  | 0 | 563627 | 0 | 0
| Div 12 | FURNISHINGS
| 12 20 00 | window coverings |  | 0 | 0 | 13384
| 12 31 00 | metal casework |  | 0 | 0 | 0
| 12 32 16 | plastic laminate casework |  | 0 | 0 | 0
| 12 61 00 | auditorium seating |  | 0 | 0 | 0
| 12 93 13 | bike racks |  | 0 | 0 | 9460
| 12 93 23 | trash enclosures |  | 0 | 0 | With Mason
| 0.09933% | Division 12 total |  |  | 0 | 22844 | 0 | 0
| Div 13 | SPECIAL CONST
| 13 00 00 | equipment/storage enclosures |  | 0 | 0 | 0
| 13 11 00 | swimming pools |  | 0 | 0 | 0
| 13 34 16 | bleachers |  | 0 | 0 | 0
| 13 34 19 | metal buildings |  | 0 | 0 | 0
| 0% | Division 13 total |  |  | 0 | 0 | 0 | 0
| Div 14 | CONVEYING
| 14 00 00 | material handling |  | 0 | 0 | 0
| 14 20 00 | elevators |  | 0 | 0 | 0
| 14 42 00 | wheelchair lifts |  | 0 | 0 | 0
| 0% | Division 14 total |  |  | 0 | 0 | 0 | 0
| Div 21 | FIRE SUPPRESSION
| 21 10 00 | fire protection/sprinklers |  | 0 | 0 | 175141
| 0.7615% | Division 21 total |  |  | 0 | 175141 | 0 | 0
| Div 22 | PLUMBING
| 22 11 00 | supply piping |  | 0 | 0 | 951959
| 22 13 00 | waste water piping |  | 0 | 0 | Incl with Plumbing
| 22 31 00 | water treatment (softner) |  | 0 | 0 | Incl with Plumbing
| 22 32 00 | water treatment (filtered) |  | 0 | 0 | Incl with Plumbing
| 22 35 00 | water heaters |  | 0 | 0 | Incl with Plumbing
| 22 42 00 | plumbing fixtures |  | 0 | 0 | Incl with Plumbing
| 4.139% | Division 22 total |  |  | 0 | 951959 | 0 | 0
| Div 23 | MECHANICAL
| 23 07 13 | mechanical insulation |  | 0 | 0 | Incl With Mechanical
| 23 50 00 | HVAC - central plant (cooling) |  | 0 | 0 | 3048562
| 23 60 00 | HVAC - central plant (heating) |  | 0 | 0 | Incl With Mechanical
| 23 76 00 | HVAC - evaporative |  | 0 | 0 | Incl With Mechanical
| 23 80 00 | HVAC - package units |  | 0 | 0 | Incl With Mechanical
| 23 81 26 | HVAC - split system |  | 0 | 0 | Incl With Mechanical
| 13.26% | Division 23 total |  |  | 0 | 3048562 | 0 | 0
| Div 25 | INTEGRATED AUTOMATION
| 25 50 00 | EMS |  | 0 | 0 | Incl With Mechanical
| 0% | Division 25 total |  |  | 0 | 0 | 0 | 0
| Div 26 | ELECTRICAL
| 26 10 00 | site electrical |  | 0 | 0 | 1642508 |  | 275000
| 26 10 00 | electrical |  | 0 | 0 | Incl with electrical
| 26 30 00 | generators |  | 0 | 0 | 0
| 26 56 00 | exterior lighting |  | 0 | 0 | Incl with electrical
| 7.142% | Division 26 total |  |  | 0 | 1642508 | 0 | 275000
| Div 27 | COMMUNICATIONS
| 27 20 00 | data cabling |  | 0 | 0 | 456022
| 27 24 00 | TV cabling |  | 0 | 0 | With Data Cabling
| 27 30 00 | intercom |  | 0 | 0 | With Data Cabling
| 27 32 13 | communications/phone |  | 0 | 0 | With Data Cabling
| 1.983% | Division 27 total |  |  | 0 | 456022 | 0 | 0
| Div 28 | SAFETY AND SECURITY
| 28 10 00 | security system |  | 0 | 0 | 53567
| 28 20 00 | surveillance/alarm |  | 0 | 0 | With Security
| 28 31 00 | fire alarm system |  | 0 | 0 | With Elecrical
| 0.2329% | Division 28 total |  |  | 0 | 53567 | 0 | 0
| Div 31 | EARTHWORK
| 31 23 00 | earthwork/mass excavation |  | 0 | 0 | 89737 | 426417 | 368174
| 31 23 00 | import/export dirt |  | 0 | 0 | With Earthwork
| 31 31 00 | soil treatment - termite |  | 0 | 0 | With Concrete
| 2.868% | Division 31 total |  |  | 0 | 89737 | 426417 | 368174
| Div 32 | EXTERIOR IMPROVEMENTS
| 32 00 00 | parking |  | 0 | 0 | With Earthwork
| 32 00 00 | unusal site conditions |  | 0 | 0 | With Earthwork
| 32 10 00 | asphalt/paving |  | 0 | 0 | With Earthwork |  | 150000
| 32 13 00 | site concrete |  | 0 | 0 | 324798 | 469405 | 218267
| 32 13 00 | sidewalks |  | 0 | 0 | With Site concrete
| 32 17 00 | striping/signage |  | 0 | 0 | With Earthwork
| 32 31 13 | chainlink fencing |  | 0 | 0 | With Wrought Iron
| 32 31 19 | wrought iron fencing |  | 0 | 0 | 0
| 32 32 00 | retaining walls |  | 0 | 0 | With Masonry
| 32 80 00 | irrigation |  | 0 | 0 | With Landscaping
| 32 90 00 | landscaping |  | 0 | 0 | 303579
| 2.732% | Division 32 total |  |  | 0 | 628377 | 469405 | 368267
| Div 33 | UTILITIES
| 33 00 00 | site utilities |  | 0 | 0 | 473651 |  | 243393
| 33 21 00 | wells |  | 0 | 0 | 0
| 33 32 16 | lift station |  | 0 | 0 | 0
| 33 36 00 | septic system |  | 0 | 0 | 0
| 33 40 00 | stormwater/drainage |  | 0 | 0 | 0 |  | 225261
| 33 49 23 | drywells |  | 0 | 0 | 125590
| 4.643% | Division 33 total |  |  | 0 | 599241 | 0 | 468654
|  | Subtotal | 20191853 |  | 0 | 17696856 | 940148 | 1554849
|  | Contractor Fee |  |  | 0 | 764032 | 44918 | 74286
|  | Contactor Contingency |  |  | 0 | 356293 | 17967 | 29714
|  | Builders Risk/Liability Insurance |  |  | 0 | 189034 | 9596 | 15871
|  | Performance & Payment Bonds |  |  | 0 | 132283 | 6715 | 11106
|  | Sales Tax |  |  | 0 | 1018037 | 51680 | 85471
|  | Subtotal | 22998856 |  | 0 | 20156535 | 1071024 | 1771297
|  | Grand Guaranteed Maximum Price (GMP) | 22998856 |  | (Total of SFB Base Cost and District Cost)