## SFB NC600-16
ADJACENT WAYS
SFB AW 200-18 |  |  | SCHEDULE OF VALUES
|  | School District | Cartwright School District #83
SFB Project Number
|  | Architect Name | ADM Group, Inc.
|  | CM @ Risk Name | RYTAN Construction
|  | County | Maricopa
|  | Permitting (Name of County/City) | City of Phoenix
[6 empty] | 0 | AW-Y
|  | GMP | 227856 |  |  |  | AW-N
|  |  |  | Cost per |  | Other On-Site
|  | = Cells to be completed - as required |  | Unit | District | Funding | Off-Site
|  |  | Quantity | (no markup) | Cost | (Adjacent Ways, etc.) | Adjacent Ways
| Div 1 | GENERAL REQUIREMENTS
| 01 45 23 | testing and inspecting | 1 |  | 12500
| 01 50 00 | tempory facilites | 1 |  | 4900
| 01 56 19 | dust control | 1 |  | 1200
| 01 57 13 | track off pads | 1 |  | 2800
|  | Division 1 total | 21400 |  | 21400 | 0 | 0
| Div 2 | EXISTING CONDITIONS
| 02 21 13 | survey | 1 |  | 11500
| 02 41 13 | site demolition/removal | 1 |  |  | 9345 | 5655
| 02 60 00 | soil treatment
|  | Division 2 total | 26500 |  | 11500 | 9345 | 5655
| Div 3 | CONCRETE
| 03 00 00 | footings/walls | 1 |  | 850
| 03 00 00 | building
| 03 20 00 | rebar
| 03 30 53 | slabs
| 03 35 00 | sealed floors
| 03 40 00 | precast concrete
|  | Division 3 total | 850 |  | 850 | 0 | 0
| Div 4 | MASONRY
| 04 00 00 | masonry walls
| 04 00 00 | masonry columns
| 04 05 19 | rebar
| 04 22 00 | site masonry
| 04 22 00 | block fencing
| 04 43 00 | stonework
|  | Division 4 total | 0 |  | 0 | 0 | 0
| Div 5 | METALS
| 05 00 00 | miscellaneous steel
| 05 10 00 | structural steel
| 05 30 00 | metal decking
| 05 51 00 | stairs
| 05 70 00 | architectural steel
|  | Division 5 total | 0 |  | 0 | 0 | 0
| Div 6 | WOODS/PLASTICS/COMPOSITES
| 06 10 00 | rough carpentry structure
| 06 15 00 | wood decking
| 06 20 00 | finish carpentry
| 06 40 00 | millwork/casework
| 06 60 00 | plastic/glass fiber
|  | Division 6 total | 0 |  | 0 | 0 | 0
| Div 7 | THERMAL/MOISTURE
| 07 10 00 | waterproofing/dampproofing
| 07 20 00 | building insulation
| 07 21 00 | foam roof
| 07 25 00 | weather barrier
| 07 31 00 | roof shingles
| 07 32 00 | roof tiles
| 07 50 00 | membrane roofing
| 07 60 00 | metal roof
| 07 60 00 | general sheet metal
| 07 72 00 | roof accessories
| 07 81 00 | sprayed fireproofing
| 07 84 00 | firestopping
| 07 95 00 | roof expansion joint
| 07 92 00 | joint sealants
|  | Division 7 total | 0 |  | 0 | 0 | 0
| Div 8 | OPENINGS
| 81 10 00 | doors & frames
| 08 33 00 | overhead doors
| 08 40 00 | storefronts
| 08 44 00 | curtain walls
| 08 50 00 | windows
| 08 60 00 | skylights
| 08 70 00 | hardware
| 08 71 13 | automatic doors
| 08 79 00 | knox box
| 08 80 00 | glass & glazing
|  | Division 8 total | 0 |  | 0 | 0 | 0
| Div 9 | FINISHES
| 09 24 00 | stucco/EIFS systems
| 09 20 00 | interior metal studs/gypsum board
| 09 22 00 | exterior metal stud framing
| 09 23 00 | decorative plaster
| 09 51 00 | acoustical ceilings
| 09 31 00 | ceramic tile
| 09 65 00 | resilient flooring
| 09 68 00 | carpet
| 09 64 00 | wood floors
| 09 67 00 | epoxy
| 09 80 00 | sound panels
| 09 90 00 | painting
| 09 77 00 | fiberglass reinforced panels
|  | Division 9 total | 0 |  | 0 | 0 | 0
| Div 10 | SPECIALTIES
| 10 11 00 | visual display boards
| 10 14 00 | signage | 1 |  |  | 4500
| 10 21 13 | toilet partitions & accessories
| 10 21 23 | cubicle track & curtain
| 10 22 26 | operable partitions/walls
| 10 26 00 | wall protection
| 10 44 00 | fire exttinguishers & cabinets
| 10 50 00 | lockers
| 10 56 13 | storage shelving
| 10 73 00 | shelters
| 10 73 13 | awnings
| 10 73 13 | canopy/ramada
| 10 75 00 | flagpoles
|  | Division 10 total | 4500 |  | 0 | 4500 | 0
| Div 11 | EQUIPMENT
| 11 16 16 | floor safe
| 11 41 00 | kitchen equipment
| 11 51 00 | library equipment
| 11 52 00 | audio/visual equipment
| 11 52 13 | projection screens
| 11 53 13 | fume hoods
| 11 61 43 | stage curtain/equipment
| 11 66 00 | sports/PE equipment
| 11 68 00 | playground equipment
| 11 68 23 | site basketball courts
| 11 68 33 | ballfield backstop
| 11 68 33 | sports fields
|  | Division 11 total | 0 |  | 0 | 0 | 0
| Div 12 | FURNISHINGS
| 12 20 00 | window coverings
| 12 31 00 | metal casework
| 12 32 16 | plastic laminate casework
| 12 61 00 | auditorium seating
| 12 93 13 | bike racks
| 12 93 23 | trash enclosures
|  | Division 12 total | 0 |  | 0 | 0 | 0
| Div 13 | SPECIAL CONST
| 13 00 00 | equipment/storage enclosures
| 13 11 00 | swimming pools
| 13 34 16 | bleachers
| 13 34 19 | metal buildings
|  | Division 13 total | 0 |  | 0 | 0 | 0
| Div 14 | CONVEYING
| 14 00 00 | material handling
| 14 20 00 | elevators
| 14 42 00 | wheelchair lifts
|  | Division 14 total | 0 |  | 0 | 0 | 0
| Div 21 | FIRE SUPPRESSION
| 21 10 00 | fire protection/sprinklers
|  | Division 21 total | 0 |  | 0 | 0 | 0
| Div 22 | PLUMBING
| 22 11 00 | supply piping
| 22 13 00 | waste water piping
| 22 31 00 | water treatment (softner)
| 22 32 00 | water treatment (filtered)
| 22 35 00 | water heaters
| 22 42 00 | plumbing fixtures
|  | Division 22 total | 0 |  | 0 | 0 | 0
| Div 23 | MECHANICAL
| 23 07 13 | mechanical insulation
| 23 50 00 | HVAC - central plant (cooling)
| 23 60 00 | HVAC - central plant (heating)
| 23 76 00 | HVAC - evaporative
| 23 80 00 | HVAC - package units
| 23 81 26 | HVAC - split system
|  | Division 23 total | 0 |  | 0 | 0 | 0
| Div 25 | INTEGRATED AUTOMATION
| 25 50 00 | EMS
|  | Division 25 total | 0 |  | 0 | 0 | 0
| Div 26 | ELECTRICAL
| 26 10 00 | site electrical
| 26 10 00 | electrical
| 26 30 00 | generators
| 26 56 00 | exterior lighting
|  | Division 26 total | 0 |  | 0 | 0 | 0
| Div 27 | COMMUNICATIONS
| 27 20 00 | data cabling
| 27 24 00 | TV cabling
| 27 30 00 | intercom
| 27 32 13 | communications/phone
|  | Division 27 total | 0 |  | 0 | 0 | 0
| Div 28 | SAFETY AND SECURITY
| 28 10 00 | security system
| 28 20 00 | surveillance/alarm
| 28 31 00 | fire alarm system
|  | Division 28 total | 0 |  | 0 | 0 | 0
| Div 31 | EARTHWORK
| 31 23 00 | earthwork/mass excavation | 1 |  |  | 33870
| 31 23 00 | import/export dirt | 474 |  |  | 7850
| 31 31 00 | soil treatment - termite
|  | Division 31 total | 41720 |  | 0 | 41720 | 0
| Div 32 | EXTERIOR IMPROVEMENTS
| 32 00 00 | parking
| 32 00 00 | unusal site conditions
| 32 10 00 | asphalt/paving | 650 |  |  | 24672
| 32 13 00 | site concrete | 2347 |  |  | 16570 | 6698
| 32 13 00 | sidewalks | 1608 |  | 9295
| 32 17 00 | striping/signage | 1 |  |  | 3375
| 32 31 13 | chainlink fencing | 1 |  | 9730
| 32 31 19 | wrought iron fencing
| 32 32 00 | retaining walls
| 32 80 00 | irrigation
| 32 90 00 | landscaping | 1 |  | 7265
|  | Division 32 total | 77605 |  | 26290 | 44617 | 6698
| Div 33 | UTILITIES
| 33 00 00 | site utilities
| 33 21 00 | wells
| 33 32 16 | lift station
| 33 36 00 | septic system
| 33 40 00 | stormwater/drainage
| 33 49 23 | drywells
|  | Division 33 total | 0 |  | 0 | 0 | 0
|  | Subtotal | 172575 |  | 60040 | 100182 | 12353
|  | A/E Fee |  | 0
| 6.95% | Contractor Fee |  | 15835 | 5509 | 9203 | 1123
|  | Project Manager Fee |  | 0
|  | General Condtions |  | 25092 | 8730 | 14566 | 1796
| 0% | Contactor Contingency |  | 0
| 0.7048% | Builders Risk/Liability Insurance |  | 1606 | 559 | 932 | 115
| 0% | Performance & Payment Bonds |  | 0
| 5.595% | Sales Tax |  | 12748 | 4434 | 7402 | 912
|  | Subtotal | 55281 |  | 19232 | 32103 | 3946
|  | Grand Guaranteed Maximum Price (GMP) | 227856