## SFB NC600-16
SFB AW 200-18 |  | SCHEDULE OF VALUES
FOR ADJACENT WAYS VALIDATION
Instructions: 1. Please enter the information requested in Rows 5-9 in the Blue cells below. 2. Based on the source of funding (On-Site Adjacent Ways, Off-Site Adjacent Ways or District Cost) enter the cost of each item in the schedule below. Allowable On-Site Adjacent Ways, Off-Site Adjacent Ways and District Cost items are in Orange. Excluded On-Site Adjacent Ways items are Gray and are intentionally locked.
| School District | Roosevelt School District
| County | Maricopa County
| SFB Adjacent Ways ID Number | (enter 4 digit ID number)
| Architect Name | Orcutt Winslow
| Contractor Name | Chasse Building Team
|  | District | On-Site | Off-Site
|  | Cost | Adjacent Ways | Adjacent Ways
Div 1 | GENERAL REQUIREMENTS
01 45 23 | testing and inspecting | 45000 |  | 10000
01 50 00 | tempory facilites | 233824 |  | 16857
01 56 19 | dust control
01 57 13 | track off pads
| Division 1 total | 278824 | 0 | 26857
Div 2 | EXISTING CONDITIONS
02 21 13 | survey | 43102 | 3565 | 5891
02 41 13 | site demolition/removal | 676366 |  | 9526
02 60 00 | soil treatment
| Division 2 total | 719468 | 3565 | 15417
Div 3 | CONCRETE
03 00 00 | footings/walls | 1594115
03 00 00 | building
03 20 00 | rebar
03 30 53 | slabs |  |  | 258495
03 35 00 | sealed floors
03 40 00 | precast concrete
| Division 3 total | 1594115 | 0 | 258495
Div 4 | MASONRY
04 00 00 | masonry walls | 927746
04 00 00 | masonry columns
04 05 19 | rebar
04 22 00 | site masonry
04 22 00 | block fencing
04 43 00 | stonework
| Division 4 total | 927746 | 0 | 0
Div 5 | METALS
05 00 00 | miscellaneous steel
05 10 00 | structural steel | 1766903
05 30 00 | metal decking
05 51 00 | stairs
05 70 00 | architectural steel
| Division 5 total | 1766903 | 0 | 0
Div 6 | WOODS/PLASTICS/COMPOSITES
06 10 00 | rough carpentry structure | 1211002
06 15 00 | wood decking
06 20 00 | finish carpentry
06 40 00 | millwork/casework | 316895
06 60 00 | plastic/glass fiber
| Division 6 total | 1527897 | 0 | 0
Div 7 | THERMAL/MOISTURE
07 10 00 | waterproofing/dampproofing
07 20 00 | building insulation | 71313
07 21 00 | foam roof
07 25 00 | weather barrier
07 31 00 | roof shingles
07 32 00 | roof tiles
07 50 00 | membrane roofing | 819479
07 60 00 | metal roof
07 60 00 | general sheet metal | 208954
07 72 00 | roof accessories
07 81 00 | sprayed fireproofing
07 84 00 | firestopping
07 95 00 | roof expansion joint
07 92 00 | joint sealants | 186653 |  | 3534
| Division 7 total | 1286399 | 0 | 3534
Div 8 | OPENINGS
81 10 00 | doors & frames | 321430
08 33 00 | overhead doors | 249840
08 40 00 | storefronts | 707080
08 44 00 | curtain walls
08 50 00 | windows
08 60 00 | skylights
08 70 00 | hardware
08 71 13 | automatic doors
08 79 00 | knox box
08 80 00 | glass & glazing
| Division 8 total | 1278350 | 0 | 0
Div 9 | FINISHES
09 24 00 | stucco/EIFS systems | 62484
09 20 00 | interior metal studs/gypsum board | 1088040
09 22 00 | exterior metal stud framing
09 23 00 | decorative plaster
09 51 00 | acoustical ceilings | 433138
09 31 00 | ceramic tile | 187518
09 65 00 | resilient flooring | 416357
09 68 00 | carpet
09 64 00 | wood floors
09 67 00 | epoxy
09 80 00 | sound panels
09 90 00 | painting | 253925
09 77 00 | fiberglass reinforced panels
| Division 9 total | 2441462 | 0 | 0
Div 10 | SPECIALTIES
10 11 00 | visual display boards | 186159
10 14 00 | signage | 36035
10 21 13 | toilet partitions & accessories
10 21 23 | cubicle track & curtain
10 22 26 | operable partitions/walls
10 26 00 | wall protection
10 44 00 | fire exttinguishers & cabinets
10 50 00 | lockers
10 56 13 | storage shelving
10 73 00 | shelters
10 73 13 | awnings
10 73 13 | canopy/ramada
10 75 00 | flagpoles
| Division 10 total | 222194 | 0 | 0
Div 11 | EQUIPMENT
11 16 16 | floor safe
11 41 00 | kitchen equipment | 451162
11 51 00 | library equipment
11 52 00 | audio/visual equipment
11 52 13 | projection screens
11 53 13 | fume hoods
11 61 43 | stage curtain/equipment | 80300
11 66 00 | sports/PE equipment | 43050
11 68 00 | playground equipment
11 68 23 | site basketball courts
11 68 33 | ballfield backstop
11 68 33 | sports fields
| Division 11 total | 574512 | 0 | 0
Div 12 | FURNISHINGS
12 20 00 | window coverings | 81668
12 31 00 | metal casework
12 32 16 | plastic laminate casework
12 61 00 | auditorium seating
12 93 13 | bike racks | 11550
12 93 23 | trash enclosures
| Division 12 total | 93218 | 0 | 0
Div 13 | SPECIAL CONST
13 00 00 | equipment/storage enclosures
13 11 00 | swimming pools
13 34 16 | bleachers
13 34 19 | metal buildings
| Division 13 total | 0 | 0 | 0
Div 14 | CONVEYING
14 00 00 | material handling
14 20 00 | elevators | 84630
14 42 00 | wheelchair lifts
| Division 14 total | 84630 | 0 | 0
Div 21 | FIRE SUPPRESSION
21 10 00 | fire protection/sprinklers | 163201
| Division 21 total | 163201 | 0 | 0
Div 22 | PLUMBING
22 11 00 | supply piping | 878256
22 13 00 | waste water piping
22 31 00 | water treatment (softner)
22 32 00 | water treatment (filtered)
22 35 00 | water heaters
22 42 00 | plumbing fixtures
| Division 22 total | 878256 | 0 | 0
Div 23 | MECHANICAL
23 07 13 | mechanical insulation | 1747001
23 50 00 | HVAC - central plant (cooling)
23 60 00 | HVAC - central plant (heating)
23 76 00 | HVAC - evaporative
23 80 00 | HVAC - package units
23 81 26 | HVAC - split system
| Division 23 total | 1747001 | 0 | 0
Div 25 | INTEGRATED AUTOMATION
25 50 00 | EMS
| Division 25 total | 0 | 0 | 0
Div 26 | ELECTRICAL
26 10 00 | site electrical
26 10 00 | electrical | 2144565 |  | 476195
26 30 00 | generators
26 56 00 | exterior lighting
| Division 26 total | 2144565 | 0 | 476195
Div 27 | COMMUNICATIONS
27 20 00 | data cabling
27 24 00 | TV cabling
27 30 00 | intercom
27 32 13 | communications/phone
| Division 27 total | 0 | 0 | 0
Div 28 | SAFETY AND SECURITY
28 10 00 | security system
28 20 00 | surveillance/alarm
28 31 00 | fire alarm system | 196577
| Division 28 total | 196577 | 0 | 0
Div 31 | EARTHWORK
31 23 00 | earthwork/mass excavation | 643423 | 56242 | 249905
31 23 00 | import/export dirt
31 31 00 | soil treatment - termite | 3212
| Division 31 total | 646635 | 56242 | 249905
Div 32 | EXTERIOR IMPROVEMENTS
32 00 00 | parking
32 00 00 | unusal site conditions
32 10 00 | asphalt/paving
32 13 00 | fire lane site concrete |  | 93242
32 13 00 | sidewalks (only for bus drop-offs)
32 17 00 | striping/signage
32 31 13 | chainlink fencing |  |  | 24800
32 31 19 | wrought iron fencing | 215750
32 32 00 | retaining walls
32 80 00 | irrigation
32 90 00 | landscaping | 370780 |  | 28241
| Division 32 total | 586530 | 93242 | 53041
Div 33 | UTILITIES
33 00 00 | site utilities | 597465 |  | 91880
33 21 00 | wells
33 32 16 | lift station
33 36 00 | septic system
33 40 00 | stormwater/drainage
33 49 23 | drywells
| Division 33 total | 597465 | 0 | 91880
| Subtotal | 19755948 | 153049 | 1175324
| A/E Fee |  |  | 0
| Contractor Fee | 1224867 |  | 84281
| Project Manager Fee |  |  | 0
| General Conditions | 1019250 |  | 84281
| Contactor Contingency | 489946 |  | 50568
| Builders Risk/Liability Insurance | 440952 |  | 30341
| Performance & Payment Bonds | 269471 |  | 18542
| Sales Tax | 1296904 |  | 89238
| Subtotal | 4741390 | 0 | 357251
| Grand Subtotal | 24497338 | 153049 | 1532575
| Project Grand Total | 26182962
| Adjacent Ways Grand Total | 1685624