## SFB NC600-16
SFB AW 200-18 |  | SCHEDULE OF VALUES
FOR ADJACENT WAYS VALIDATION
Instructions: 1. Please enter the information requested in Rows 5-9 in the Blue cells below. 2. Based on the source of funding (On-Site Adjacent Ways, Off-Site Adjacent Ways or District Cost) enter the cost of each item in the schedule below. Allowable On-Site Adjacent Ways, Off-Site Adjacent Ways and District Cost items are in Orange. Excluded On-Site Adjacent Ways items are Gray and are intentionally locked.
| School District | Phoenix Union High School District
| County | Maricopa
| SFB Adjacent Ways ID Number | (enter 4 digit ID number)
| Architect Name | SPS+
| Contractor Name | CHASSE Building Team
|  | District | On-Site | Off-Site
|  | Cost | Adjacent Ways | Adjacent Ways
Div 1 | GENERAL REQUIREMENTS
01 45 23 | testing and inspecting | 45000 |  | 8626
01 50 00 | tempory facilites | 154296 |  | 27229
01 56 19 | dust control
01 57 13 | track off pads
| Division 1 total | 199296 | 0 | 35855
Div 2 | EXISTING CONDITIONS
02 21 13 | survey | 51376 | 7900 | 2100
02 41 13 | site demolition/removal | 209104 | 36900 | 8100
02 60 00 | soil treatment
| Division 2 total | 260480 | 44800 | 10200
Div 3 | CONCRETE
03 00 00 | footings/walls
03 00 00 | building | 1174501
03 20 00 | rebar
03 30 53 | slabs
03 35 00 | sealed floors
03 40 00 | precast concrete
| Division 3 total | 1174501 | 0 | 0
Div 4 | MASONRY
04 00 00 | masonry walls | 772279
04 00 00 | masonry columns
04 05 19 | rebar
04 22 00 | site masonry
04 22 00 | block fencing
04 43 00 | stonework
| Division 4 total | 772279 | 0 | 0
Div 5 | METALS
05 00 00 | miscellaneous steel | 35000
05 10 00 | structural steel | 1253084
05 30 00 | metal decking
05 51 00 | stairs
05 70 00 | architectural steel
| Division 5 total | 1288084 | 0 | 0
Div 6 | WOODS/PLASTICS/COMPOSITES
06 10 00 | rough carpentry structure | 22450
06 15 00 | wood decking
06 20 00 | finish carpentry
06 40 00 | millwork/casework | 160697
06 60 00 | plastic/glass fiber
| Division 6 total | 183147 | 0 | 0
Div 7 | THERMAL/MOISTURE
07 10 00 | waterproofing/dampproofing
07 20 00 | building insulation | 29667
07 21 00 | foam roof
07 25 00 | weather barrier
07 31 00 | roof shingles
07 32 00 | roof tiles
07 50 00 | membrane roofing | 356860
07 60 00 | metal roof
07 60 00 | general sheet metal | 73248
07 72 00 | roof accessories
07 81 00 | sprayed fireproofing
07 84 00 | firestopping
07 95 00 | roof expansion joint
07 92 00 | joint sealants | 69264
| Division 7 total | 529039 | 0 | 0
Div 8 | OPENINGS
81 10 00 | doors & frames | 273496
08 33 00 | overhead doors | 82769
08 40 00 | storefronts
08 44 00 | curtain walls
08 50 00 | windows
08 60 00 | skylights
08 70 00 | hardware
08 71 13 | automatic doors
08 79 00 | knox box
08 80 00 | glass & glazing | 135325
| Division 8 total | 491590 | 0 | 0
Div 9 | FINISHES
09 24 00 | stucco/EIFS systems
09 20 00 | interior metal studs/gypsum board | 372809
09 22 00 | exterior metal stud framing
09 23 00 | decorative plaster
09 51 00 | acoustical ceilings | 65935
09 31 00 | ceramic tile | 39143
09 65 00 | resilient flooring | 126469
09 68 00 | carpet
09 64 00 | wood floors
09 67 00 | epoxy
09 80 00 | sound panels
09 90 00 | painting | 125176
09 77 00 | fiberglass reinforced panels
| Division 9 total | 729532 | 0 | 0
Div 10 | SPECIALTIES
10 11 00 | visual display boards | 1327
10 14 00 | signage | 30000
10 21 13 | toilet partitions & accessories | 36481
10 21 23 | cubicle track & curtain
10 22 26 | operable partitions/walls | 29025
10 26 00 | wall protection | 16204
10 44 00 | fire exttinguishers & cabinets | 4208
10 50 00 | lockers | 5800
10 56 13 | storage shelving
10 73 00 | shelters
10 73 13 | awnings
10 73 13 | canopy/ramada
10 75 00 | flagpoles | 16416
| Division 10 total | 139461 | 0 | 0
Div 11 | EQUIPMENT
11 16 16 | floor safe
11 41 00 | kitchen equipment
11 51 00 | library equipment
11 52 00 | audio/visual equipment
11 52 13 | projection screens
11 53 13 | fume hoods
11 61 43 | stage curtain/equipment
11 66 00 | sports/PE equipment
11 68 00 | playground equipment
11 68 23 | site basketball courts
11 68 33 | ballfield backstop
11 68 33 | sports fields
| Division 11 total | 0 | 0 | 0
Div 12 | FURNISHINGS
12 20 00 | window coverings
12 31 00 | metal casework
12 32 16 | plastic laminate casework
12 61 00 | auditorium seating
12 93 13 | bike racks
12 93 23 | trash enclosures
| Division 12 total | 0 | 0 | 0
Div 13 | SPECIAL CONST
13 00 00 | equipment/storage enclosures | 1486401
13 11 00 | swimming pools
13 34 16 | bleachers
13 34 19 | metal buildings
| Division 13 total | 1486401 | 0 | 0
Div 14 | CONVEYING
14 00 00 | material handling
14 20 00 | elevators | 118647
14 42 00 | wheelchair lifts
| Division 14 total | 118647 | 0 | 0
Div 21 | FIRE SUPPRESSION
21 10 00 | fire protection/sprinklers | 88350
| Division 21 total | 88350 | 0 | 0
Div 22 | PLUMBING
22 11 00 | supply piping
22 13 00 | waste water piping
22 31 00 | water treatment (softner)
22 32 00 | water treatment (filtered)
22 35 00 | water heaters
22 42 00 | plumbing fixtures | 472200
| Division 22 total | 472200 | 0 | 0
Div 23 | MECHANICAL
23 07 13 | mechanical insulation
23 50 00 | HVAC - central plant (cooling)
23 60 00 | HVAC - central plant (heating)
23 76 00 | HVAC - evaporative
23 80 00 | HVAC - package units | 772798
23 81 26 | HVAC - split system
| Division 23 total | 772798 | 0 | 0
Div 25 | INTEGRATED AUTOMATION
25 50 00 | EMS
| Division 25 total | 0 | 0 | 0
Div 26 | ELECTRICAL
26 10 00 | site electrical | 667628 |  | 30000
26 10 00 | electrical | 964274
26 30 00 | generators
26 56 00 | exterior lighting
| Division 26 total | 1631902 | 0 | 30000
Div 27 | COMMUNICATIONS
27 20 00 | data cabling | 92967
27 24 00 | TV cabling
27 30 00 | intercom
27 32 13 | communications/phone
| Division 27 total | 92967 | 0 | 0
Div 28 | SAFETY AND SECURITY
28 10 00 | security system | 287033
28 20 00 | surveillance/alarm
28 31 00 | fire alarm system | 82118
| Division 28 total | 369151 | 0 | 0
Div 31 | EARTHWORK
31 23 00 | earthwork/mass excavation | 364046 | 210000
31 23 00 | import/export dirt | 15000 | 15000
31 31 00 | soil treatment - termite | 1480
| Division 31 total | 380526 | 225000 | 0
Div 32 | EXTERIOR IMPROVEMENTS
32 00 00 | parking
32 00 00 | unusal site conditions
32 10 00 | asphalt/paving | 739126 | 115000
32 13 00 | fire lane site concrete |  | 152500
32 13 00 | sidewalks (only for bus drop-offs)
32 17 00 | striping/signage |  | 25000
32 31 13 | chainlink fencing
32 31 19 | wrought iron fencing | 63082
32 32 00 | retaining walls
32 80 00 | irrigation
32 90 00 | landscaping | 134615
| Division 32 total | 936823 | 292500 | 0
Div 33 | UTILITIES
33 00 00 | site utilities | 1078736 |  | 15000
33 21 00 | wells
33 32 16 | lift station
33 36 00 | septic system
33 40 00 | stormwater/drainage
33 49 23 | drywells | 78420
| Division 33 total | 1157156 | 0 | 15000
| Subtotal | 13274330 | 562300 | 91055
A/E Fee
| Contractor Fee | 833594 | 38501 | 9031
Project Manager Fee
| General Conditions | 866894 | 123915 | 29066
| Contactor Contingency | 375118 | 17325 | 4064
| Builders Risk/Liability Insurance | 300094 | 13861 | 3251
| Performance & Payment Bonds | 183391 | 8470 | 1987
| Sales Tax | 838490 | 38727 | 9084
| Subtotal | 3397581 | 240799 | 56483
| Grand Subtotal | 16671911 | 803099 | 147538
| Project Grand Total | 17622548
| Adjacent Ways Grand Total | 950637