## SFB NC600-16
SFB AW 200-18 |  | SCHEDULE OF VALUES
FOR ADJACENT WAYS VALIDATION
Instructions: 1. Please enter the information requested in Rows 5-9 in the Blue cells below. 2. Based on the source of funding (On-Site Adjacent Ways, Off-Site Adjacent Ways or District Cost) enter the cost of each item in the schedule below. Allowable On-Site Adjacent Ways, Off-Site Adjacent Ways and District Cost items are in Orange. Excluded On-Site Adjacent Ways items are Gray and are intentionally locked.
| School District | Somerton School District #11
| County | Somerton
| SFB Adjacent Ways ID Number | (enter 4 digit ID number)
| Architect Name | DLR Group
| Contractor Name | Pilkington Construction Co.
|  | District | On-Site | Off-Site
|  | Cost | Adjacent Ways | Adjacent Ways
Div 1 | GENERAL REQUIREMENTS
01 45 23 | testing and inspecting | 32000
01 50 00 | tempory facilites | 111054.91
01 56 19 | dust control | 13000
01 57 13 | track off pads | 30445.09
| Division 1 total | 186500 | 0 | 0
Div 2 | EXISTING CONDITIONS
02 21 13 | survey | 3000
02 41 13 | site demolition/removal | 4500
02 60 00 | soil treatment | 3000
| Division 2 total | 10500 | 0 | 0
Div 3 | CONCRETE
03 00 00 | footings/walls
03 00 00 | building | 187961 |  | 60636
03 20 00 | rebar
03 30 53 | slabs | 1350
03 35 00 | sealed floors | 3900
03 40 00 | precast concrete
| Division 3 total | 193211 | 0 | 60636
Div 4 | MASONRY
04 00 00 | masonry walls
04 00 00 | masonry columns
04 05 19 | rebar
04 22 00 | site masonry
04 22 00 | block fencing
04 43 00 | stonework
| Division 4 total | 0 | 0 | 0
Div 5 | METALS
05 00 00 | miscellaneous steel | 850
05 10 00 | structural steel | 2000
05 30 00 | metal decking
05 51 00 | stairs | 753
05 70 00 | architectural steel | 2400
| Division 5 total | 6003 | 0 | 0
Div 6 | WOODS/PLASTICS/COMPOSITES
06 10 00 | rough carpentry structure | 200000
06 15 00 | wood decking | 19000
06 20 00 | finish carpentry | 13141.1
06 40 00 | millwork/casework | 5631.9
06 60 00 | plastic/glass fiber
| Division 6 total | 237773 | 0 | 0
Div 7 | THERMAL/MOISTURE
07 10 00 | waterproofing/dampproofing | 4300
07 20 00 | building insulation | 72125
07 21 00 | foam roof | 29564.67
07 25 00 | weather barrier | 14577.67
07 31 00 | roof shingles | 14577.67
07 32 00 | roof tiles | 14577.67
07 50 00 | membrane roofing | 14577.67
07 60 00 | metal roof | 14577.67
07 60 00 | general sheet metal
07 72 00 | roof accessories | 600
07 81 00 | sprayed fireproofing
07 84 00 | firestopping
07 95 00 | roof expansion joint | 4300
07 92 00 | joint sealants | 4300
| Division 7 total | 188078.02 | 0 | 0
Div 8 | OPENINGS
81 10 00 | doors & frames | 17684
08 33 00 | overhead doors | 9205
08 40 00 | storefronts | 11574
08 44 00 | curtain walls
08 50 00 | windows | 5000
08 60 00 | skylights
08 70 00 | hardware | 23368
08 71 13 | automatic doors
08 79 00 | knox box
08 80 00 | glass & glazing
| Division 8 total | 66831 | 0 | 0
Div 9 | FINISHES
09 24 00 | stucco/EIFS systems | 156612.57
09 20 00 | interior metal studs/gypsum board | 10152.25
09 22 00 | exterior metal stud framing | 10152.25
09 23 00 | decorative plaster
09 51 00 | acoustical ceilings | 30152.25
09 31 00 | ceramic tile | 20115
09 65 00 | resilient flooring
09 68 00 | carpet | 17719.68
09 64 00 | wood floors
09 67 00 | epoxy
09 80 00 | sound panels
09 90 00 | painting | 14445
09 77 00 | fiberglass reinforced panels
| Division 9 total | 259349 | 0 | 0
Div 10 | SPECIALTIES
10 11 00 | visual display boards | 4000
10 14 00 | signage | 1560
10 21 13 | toilet partitions & accessories | 10794
10 21 23 | cubicle track & curtain
10 22 26 | operable partitions/walls
10 26 00 | wall protection
10 44 00 | fire exttinguishers & cabinets | 2811
10 50 00 | lockers
10 56 13 | storage shelving
10 73 00 | shelters
10 73 13 | awnings
10 73 13 | canopy/ramada
10 75 00 | flagpoles
| Division 10 total | 19165 | 0 | 0
Div 11 | EQUIPMENT
11 16 16 | floor safe
11 41 00 | kitchen equipment
11 51 00 | library equipment
11 52 00 | audio/visual equipment
11 52 13 | projection screens
11 53 13 | fume hoods
11 61 43 | stage curtain/equipment
11 66 00 | sports/PE equipment
11 68 00 | playground equipment
11 68 23 | site basketball courts
11 68 33 | ballfield backstop
11 68 33 | sports fields
| Division 11 total | 0 | 0 | 0
Div 12 | FURNISHINGS
12 20 00 | window coverings
12 31 00 | metal casework
12 32 16 | plastic laminate casework
12 61 00 | auditorium seating
12 93 13 | bike racks
12 93 23 | trash enclosures
| Division 12 total | 0 | 0 | 0
Div 13 | SPECIAL CONST
13 00 00 | equipment/storage enclosures
13 11 00 | swimming pools
13 34 16 | bleachers
13 34 19 | metal buildings
| Division 13 total | 0 | 0 | 0
Div 14 | CONVEYING
14 00 00 | material handling
14 20 00 | elevators
14 42 00 | wheelchair lifts
| Division 14 total | 0 | 0 | 0
Div 21 | FIRE SUPPRESSION
21 10 00 | fire protection/sprinklers | 32055
| Division 21 total | 32055 | 0 | 0
Div 22 | PLUMBING
22 11 00 | supply piping
22 13 00 | waste water piping
22 31 00 | water treatment (softner)
22 32 00 | water treatment (filtered)
22 35 00 | water heaters
22 42 00 | plumbing fixtures | 127941.27
| Division 22 total | 127941.27 | 0 | 0
Div 23 | MECHANICAL
23 07 13 | mechanical insulation
23 50 00 | HVAC - central plant (cooling) | 65902
23 60 00 | HVAC - central plant (heating) | 65902
23 76 00 | HVAC - evaporative | 65902
23 80 00 | HVAC - package units
23 81 26 | HVAC - split system
| Division 23 total | 197706 | 0 | 0
Div 25 | INTEGRATED AUTOMATION
25 50 00 | EMS
| Division 25 total | 0 | 0 | 0
Div 26 | ELECTRICAL
26 10 00 | site electrical
26 10 00 | electrical | 246540
26 30 00 | generators
26 56 00 | exterior lighting
| Division 26 total | 246540 | 0 | 0
Div 27 | COMMUNICATIONS
27 20 00 | data cabling
27 24 00 | TV cabling
27 30 00 | intercom
27 32 13 | communications/phone
| Division 27 total | 0 | 0 | 0
Div 28 | SAFETY AND SECURITY
28 10 00 | security system
28 20 00 | surveillance/alarm
28 31 00 | fire alarm system | 12691
| Division 28 total | 12691 | 0 | 0
Div 31 | EARTHWORK
31 23 00 | earthwork/mass excavation
31 23 00 | import/export dirt
31 31 00 | soil treatment - termite | 1200
| Division 31 total | 1200 | 0 | 0
Div 32 | EXTERIOR IMPROVEMENTS
32 00 00 | parking
32 00 00 | unusal site conditions
32 10 00 | asphalt/paving
32 13 00 | fire lane site concrete
32 13 00 | sidewalks (only for bus drop-offs)
32 17 00 | striping/signage
32 31 13 | chainlink fencing | 4200
32 31 19 | wrought iron fencing
32 32 00 | retaining walls
32 80 00 | irrigation
32 90 00 | landscaping
| Division 32 total | 4200 | 0 | 0
Div 33 | UTILITIES
33 00 00 | site utilities
33 21 00 | wells
33 32 16 | lift station
33 36 00 | septic system
33 40 00 | stormwater/drainage
33 49 23 | drywells
| Division 33 total | 0 | 0 | 0
| Subtotal | 1789743.29 | 0 | 60636
| A/E Fee |  |  | 6638.16
| Contractor Fee | 194309
Project Manager Fee
General Conditions
Contactor Contingency
Builders Risk/Liability Insurance
| Performance & Payment Bonds | 17452
| Sales Tax | 143582.71
| Subtotal | 355343.71 | 0 | 6638.16
| Grand Subtotal | 2145087 | 0 | 67274.16
| Project Grand Total | 2212361.16
| Adjacent Ways Grand Total | 67274.16